## C. ERP Design
RACI-matrix legend:
| Initiative C. ERP Design work plan | [16 empty] | R - responsible |  |  |  |  | C - consult | [6 empty] | Development |  |  |  | Approval
| Draft version. The final version will be based on the diagnostic results. | [16 empty] | A - accountable |  |  |  |  | I - informed
|  | RACI-matrix | [6 empty] | M1 |  |  |  | M2 |  |  |  | M3 |  |  |  | M4 |  |  |  | M5 |  |  |  | M6 |  |  |  | M7
# | ACTIVITIES | KPMG | PMO | FIN | HR | PROC | DATA | IT | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | DELIVERABLES
1 | Current state assessment and business requirements definition
1.1 | Collection of inventory of information systems and automation tools for centralized functions (Procurement, Warehouse Management, Inventory Management, Human Resource Management, Accounting and Reporting), and their current business process flows (prepared by BIR Ecosystem Functions) | C | R | C | C | C |  | A | [28 empty] | Inventory of information systems and automation tools
1.2 | Interview with centralized functions (Procurement, Warehouse Management, Inventory Management, Human Resource Management, Accounting and Reporting) to understand their current processes (both centralized and not centralized) and limitations/dependencies, identify initial business requirements for target state | R | C | A | A | A | C | A | [28 empty] | - Interview schedule - Meeting minutes - Business requirements catalog format
1.3 | Preparation of complete list of business requirements by functional experts | C | A | R | R | R | C | R | [28 empty] | Catalog of business requirements
1.4 | Agree on prelimiary target ERP platform to align on target vision of centralized functions | R | C | A | A | A |  | A
1.5 | Facilitation sessions by KPMG with centralized functions to help them to design target business process flows (3-4th level) based on: - Regulatory documents and legislation for financial sector (by Central Bank) where applicable - Analysis of existing process maps and flows, policies, procedures, current automation, usage of AI in process | R | C | A | A | A |  | A | [28 empty] | Presentation on business processes design formats and approach
1.6 | Design of target business process flows by functional experts of BIR Ecosystem (supported by KPMG facilitation meetings when relevant) | C | A | R | R | R |  | C | [28 empty] | Draft target business processes
1.7 | Enrichment of target business processes (within ERP scope) by KPMG based on: - results of activity 1.5 - apllication of reference processes and functional capability maps/blueprints available for KPMG from similar projects and best practices - Available capabilities of selected 1-2 popular ERP solutions for considerations. | R | A | C | C | C | C | C | [28 empty] | Draft target business processes
1.8 | Validation session with functional leaders to confirm target business processes and business requirements | R | C | A | A | A | C | A | [28 empty] | Finalized target business processes Finalized business requirements
| Milestone: business requirements for ERP are validated |  | A
2 | Target ERP architecture design
2.1 | Design 2-3 scenarios for target ERP vision (ERP-only for all selected centralized perimeter, or ERP + other tailored solutions/automation options, or lighter tools, etc.) with achievable benefits, pros/cons and preliminary investment amount | R | C | C | C | C | C | C | [28 empty] | Target ERP scenarios/options
2.2 | Validation session with Project Leader and Functional leaders facilitated by KPMG to agree on target scenario/option | C | A | A | A | A | C | A | [28 empty] | Target ERP scenarios/options
2.3 | Design the target architecture for ERP (and automation ecosystem around ERP) for selected scenario | R | I | C | C | C | C | C | [28 empty] | Target ERP architecture
2.4 | Prepare requirements on master data for ERP, reporting types/formats, ecosystem-level system integration model through common process & data standards. | R | I | C | C | C | A, C | A, C | [28 empty] | Target ERP architecture
| Milestone: target ERP scenario/option and architecture validated |  | A
3 | ERP requirements package
3.1 | Based on all inputs from business requirements and target ERP architecture, develop RFI and detailed Request for Proposal (RFP) which includes functional, technical, integration, master data, non-functional requirements for the ERP landscape | R | A | C | C | C | C | C | [28 empty] | Draft ERP requirements package
3.2 | Jointly select potential system integrators to share RFI | C | A | I | I | I | I | C | [28 empty] | List of potential system integrators
3.3 | Pre-tender communications to validate RFP and capabilties of market vendors - advisory support by KPMG during communication with potential vendors and system integrators to ensure that RFP requirements and client expectations are clear and can be implemented | C | A | C | C | C | C | C
3.4 | Finalize ERP requirements package ready for further tender process | R | A | C | C | C | C | C | [28 empty] | ERP requirements package
| Milestone: target ERP requirements package validated |  | A
4 | Implementation roadmap
4.1 | Develop detailed action plan for the implementation of ERP, which includes for each key activity – decomposition of the activity into steps and components, work results of the activity, responsible parties/persons, timeline, milestones, success criteria/acceptance criteria, related risks, dependency between activities, etc. | R | A | C | C | C | C | C | [28 empty] | ERP implementation roadmap
4.2 | Present initiative results to the key stakeholders | R | A | I | I | I | I | I | [28 empty] | Presentation on project results
| Milestone: target ERP implementation roadmap validated |  | A
| Minumum allocated FTE | 5 | 1 | 1 | 1 | 1 | 0.2 | 1